## LOE v1.0
|  | Jump Start LOE - Site Disaster Recovery on Oracle Cloud |  | Cloud Infrastructure Specialist | Cloud Network Specialist | Project Manager | Total Man Hours | Duration | Comments/Assumptions
1 | Cloud Tenancy: Network Setup |  |  | 50 | 0 | 13 | 63 | 50
| 1.1 | VNC setup |  | 10 | 0 | 0 | 10
| 1.2 | VNC Networking |  | 5 | 0 | 0 | 5
| 1.3 | VPN Setup |  | 5 | 0 | 0 | 5
| 1.4 | Fast Connect Setup |  | 10 | 0 | 0 | 10
| 1.5 | Test Connectity for VPN and Fast Connect |  | 10 | 0 | 0 | 10
| 1.6 | Validate communication from on premise to OCI both directions |  | 10 | 0 | 0 | 10
| 1.7 | Working with Oracle Cloud Support Team for any bugs or config fixes
2 | OCI DNS Service Setup |  |  | 30 | 0 | 8 | 38 | 30
| 2.1 | DNS Service Setup |  | 10 |  | 0 | 10
| 2.2 | DNS Traffic Management |  | 5 |  | 0 | 5
| 2.3 | Configure and Test DNS Services |  | 5 |  | 0 | 5
| 2.4 | Working with Oracle Cloud Support Team for any bugs or config fixes |  | 10 |  | 0 | 10
3 | Load Balancer Service Setup & Testing |  |  | 25 | 30 | 8 | 63 | 30
| 3.1 | Setup Load Balancer |  | 5 | 5 | 0 | 10
| 3.2 | Load balancer advanced configuration |  | 5 | 5 | 0 | 10
| 3.3 | Test Laod balancer setup |  | 5 | 10 | 0 | 15
| 3.4 | Working with Oracle Cloud Support Team for any bugs or config fixes |  | 10 | 10 | 0 | 20
[6 empty] | 0 | 0
5 | BUILD - AUXILIARY SERVICES (All Phases) |  |  | 0 | 0 | 0 | 0 | 0
| 5.1 | Create NAT and Migration/Sync Tools Servers (Network Compartment) |  | 12 | 4 | 0 | 16
| 5.2 | Configure NAT Server and Update Internet Gateway Route Table and Security Lists |  | 12 | 0 | 0 | 12
| 5.3 | Stage & Install Software for Migration/Sync Tools |  | 0 | 8 | 0 | 8
| 5.4 | Configure Migration/Sync Tools Server |  | 4 | 4 | 0 | 8
6 | BUILD - APP PRODUCTION ENVIRONMENT |  |  | 0 | 0 | 0 | 0 | 0
| 6.1 | Create Compute & Database Instances (VM/DBS, Boot and Block Volumes, VNICs) |  | 4 | 2 | 0 | 6
| 6.2 | WEB nodes - Build/Migrate (WLS, PeopleTools, and Portal tech/app stack deployment) |  | 16 | 4 |  | 20
| 6.4 | APP nodes - Build/Migrate (PeopleTools, Tuxedo, Cobol, and Phire tech/app stack deployment) |  | 8 | 4 | 0 | 12
| 6.5 | UTL nodes - Build/Migrate (Process Scheduler tech/app stack deployment) |  | 8 | 4 | 0 | 12
Wave 1 - Primary Deployment for Functional Integration Testing (FIT)
| 6.6 | DATA Build/Migrate Instances (DBaaS RAC Deployment, DataPump Import, Configuration) |  | 4 | 24 | 0 | 28
| 6.7 | Patch the various Production nodes (OS, Apps, Database, etc) |  | 2 | 4 | 0 | 6
| 6.8 | Configure Web Load Balancers and Portal DNS |  | 6 | 0 | 0 | 6
** | 6.9 | FIT - Release to Customer for Functional Integration Testing |  | 2 | 2 | 0 | 4
| 6.10 | FIT - Support Customer Testing/Break/Fix |  | 16 | 32 | 0 | 48
| 6.11 | FIT - Apply Break/Fix Configruations and patches (Vendor + Customer) |  | 2 | 4 | 0 | 6
** | 6.12 | FIT - Customer Validated |  | 1 | 1 | 0 | 2
| 6.13 | Database Backup (Configure & Script Incremental Backups) |  | 0 | 8 | 0 | 8
| 6.14 | Clone Compute Instances (BRONZE) |  | 2 | 0 | 0 | 2
| 6.15 | Update the Logical Architecture & Cook Book |  | 0 | 0 | 0 | 0
Wave 2 - Secondary Deployment for System Integration Testing (SIT)
| 6.16 | DATA Replication Configurations (OnPrem to Cloud) |  |  |  | 0 | 0
| 6.17 | Patch the various Production nodes (OS, Apps, Database, etc) |  |  |  | 0 | 0
| 6.18 | Configure Web Load Balancers and Portal DNS |  |  |  | 0 | 0
| 6.19 | Configure Integration Broker with "stubbed" data files |  |  |  | 0 | 0
** | 6.20 | SIT - Release to Customer for Functional Integration Testing |  |  |  | 0 | 0
| 6.21 | SIT - Support Customer Testing/Break/Fix |  |  |  | 0 | 0
| 6.22 | SIT - Apply Break/Fix Configruations and patches (Vendor + Customer) |  |  |  | 0 | 0
** | 6.23 | SIT - Customer Validated |  |  |  | 0 | 0
| 6.24 | Database Backup (Configure & Script Incremental Backups) |  |  |  | 0 | 0
| 6.25 | Clone Compute Instances (SILVER) |  |  |  | 0 | 0
| 6.26 | Update the Logical Architecture & Cook Book |  |  |  | 0 | 0
Wave 3 - Tertiary Deployment for User Acceptance Testing (UAT)
| 6.27 | DATA Replication Configurations (OnPrem to Cloud) |  |  |  | 0 | 0
| 6.28 | Patch the various Production nodes (OS, Apps, Database, etc) |  |  |  | 0 | 0
| 6.29 | Configure Web Load Balancers and Portal DNS |  |  |  | 0 | 0
| 6.30 | Configure Integration Broker with "stubbed" data files |  |  |  | 0 | 0
** | 6.31 | UAT - Release to Customer for Functional Integration Testing |  |  |  | 0 | 0
| 6.32 | UAT - Support Customer Testing/Break/Fix |  |  |  | 0 | 0
| 6.33 | UAT - Apply Break/Fix Configruations and patches (Vendor + Customer) |  |  |  | 0 | 0
** | 6.34 | UAT - Customer Validated |  |  |  | 0 | 0
| 6.35 | Database Backup (Configure & Script Incremental Backups) |  |  |  | 0 | 0
| 6.36 | Clone Compute Instances (Configure GOLD Backups) |  |  |  | 0 | 0
| 6.37 | Update the Logical Architecture & Cook Book |  |  |  | 0 | 0
7 | RSS - Handoff |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
8 |  |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
9 |  |  |  | 0 | 0 | 0 | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
[6 empty] | 0 | 0
0
0
|  | Totals Hours |  | 105 | 48 | 34 | 187
|  | Contingency | 10% | 11 | 5 | 4 | 19 | 0
|  | Grand Total |  | 116 | 53 | 38 | 206 | 0
|  | Rate |  | 25 | 25 | 20
|  | Total Cost |  | 2900 | 1325 | 760 |  | TOTAL | 4985
|  |  | Estimated Travel Cost |  |  |  |  | TOTAL TRAVEL | 0
[8 empty] | 110 | Calendar time (hours)
[8 empty] | 3 | Calendar time (weeks)
| Option 1 | VPN for secure transfer |  | 16 | 0 | 4 | 20 | 16
| 1 | Create Internet Gateway and other required networking configurations |  | 4
| 2 | Build VPN Tunnel |  | 8
| 3 | Test connectivity from on premise to OCI |  | 4
|  | Totals Hours |  | 16 | 0 | 4 | 20
|  | Contingency | 10% | 2 | 0 | 1 | 2 | 0
|  | Grand Total |  | 18 | 0 | 5 | 22 | 0
|  | Rate |  | 30 | 30 | 20
|  | Total Cost |  | 540 | 0 | 100 |  | TOTAL | 640
| Option 2 - Offline Backup using OCI CLI |  |  | 0 | 18 | 5 | 23 | 18
| 1 | Oracle On Premise Offline Backup to Oracle Cloud |  |  | 2 | 0 | 2
| 2 | Install Oracle OCI CLI toolset on on premise server |  |  | 2 | 0 | 2
| 3 | Copy files over from local machines to Oracle Object Storage Cloud. |  |  | 10 | 0 | 10
| 5 | oci os object bulk-upload automation |  |  | 4 | 0 | 4
|  | Totals Hours |  | 0 | 18 | 5 | 23
|  | Contingency | 15% | 0 | 2 | 1 | 3 | 0
|  | Grand Total |  | 0 | 20 | 6 | 26 | 0
|  | Rate |  | 30 | 30 | 20
|  | Total Cost |  | 0 | 600 | 120 |  | TOTAL | 720
Note on I25: ====== ID#AAAAJ5BdJCE tc={8368D1DB-9B60-0849-A114-C1B66C90DEC9} (2020-09-08 15:36:16) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: v2.2: Fixed a Calc issue in this field.
Note on D30: ====== ID#AAAAJ5BdJCM tc={31A80125-55F0-7943-BA7F-748AD39BF4E8} (2020-09-08 15:36:16) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: v2.2: Removed the OEM 13c task as it’s Out of Scope for SOW.
Note on I31: ====== ID#AAAAJ5BdJCI tc={FE59687E-58B1-2741-B681-510685CCA7F7} (2020-09-08 15:36:16) [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: v2.2: Fixed a Calc issue in this field.